**The PSERN Project Radio Deployment and Transition Updates** is provided below. Please scroll down to see the circle charts.

The focus of radio deployment continues to be on portables for Wave 2 core agencies (Seattle Police/Fire, UWPD, King County DAJD, Sound Transit/KC Metro Police, and Sound Transit Safety/Security) and priority public safety agencies bordering Seattle.

·       **Wave 1 (SPU & Sound Transit Operations) is Substantially COMPLETE**

·       **Wave 2 (Seattle Area Agencies & Public Safety Portables)**

o   Radio Deployment:

~~·~~Mobiles:

~~·~~No mobile installations occurred for Wave 2 agencies during the week of March 13.

~~·~~All Wave 2-A transition agencies mobile deployments are **COMPLETE**.

~~·~~Portables:

·       672 portables were distributed to agencies last week.

~~·~~The following agencies are **COMPLETE,**and agency internal radio distribution is underway: Seattle Fire & Police, UWPD, Sound Transit Safety/Security, KC Metro Transit Police, Sound Transit Police, Mercer Island Police and Fire, & DAJD.

~~·~~Other upcoming portable deliveries from Motorola are scheduled and portable deliveries will occur within the next few weeks:

Ø  King County Airport/ARFF, KCSO, Medic One, KC Fire District 2 & 20 & 44, Kent Police, Bellevue Police & Fire, Vashon Island Fire/Rescue, Tukwila Police, Shoreline Fire, Puget Sound Regional Fire, Seattle Public Schools, City of Seattle general government agencies*,* Parks Security, KC E911, City of Kirkland, UW Medical Center & EM, Centrio Energy, Seattle Housing Authority, Shoreline Fire, Northshore Fire, Renton Regional Fire Authority & NORCOM

·       PSERN Project staff are reaching out to all agencies receiving equipment in priority order to review and confirm deployment plans.

·       Control Stations/Consolettes: No Wave 2 control stations were deployed last week.

·       **Wave 3 (Agencies south of I-90)**

o   Radio Deployment:

·       Mobiles: 48 Wave 3 mobile installations occurred last week.

~~·~~Portables: Deployment has not launched yet, although a number of public safety agencies in Wave 3 areas are getting their portables during the Wave 2 deployment.

·       Control Stations/Consolettes: Deployment has not launched yet.

·       **Future Transition Preparations**

o   Wave 2 Transition – March 28, 2023 (see comments below)

o   Wave 3 Transition – TBD but will shift to late May 2023

o   Wave 4 Transition – late June 2023

Wave 2 Transition

•        Wave 2 Transition begins on March 28 and will be split into two phases:

•        Wave 2-A – Seattle Police, Seattle Fire, UWPD, KC Metro and Sound Transit Police, KC DAJD, KC Airport/ARFF, Sound Transit Safety/Security and priority general government users (interoperate with Police/Fire).

•        Wave 2-B – Remainder of Seattle general government users, other general government users, including mobiles.

•        Wave 2-B Transition will be ~2 weeks after Wave 2-A.

·       **Other News**

* West Seattle antenna move (Seattle IBC area) was finalized on March 8 and outstanding IBC coverage testing was completed on March 22.